## Direct X UAT OBS
P2R Direct X SRE UAT OBSERVATION DETAILS
SL NO. | WF step (REQ, PO, APP, etc.) | Category | Particulars | Test Scenarios /Observations | Status/Result | Implications | Reference | DIR/IND Common? | Comments
1 | PO | Issue Fixed | HSN /TAX code | HSN & TAX code should automatically populate in the system how ever it has to be manually keyed in today | Open | Under Discussion |  | Yes | For catalog item, HSN/SAC code will come from myMall in PR custom HS Code field and same will transfer to purchase Order under control code field too for existing HSN/SAC codes else it will change to default HSN/SAC code which is 82141010. | 8500019716
2 | PO | Functional Defects | PO Creation Notification | NO notification received via mail once PR is fully approved to proceed PO Creations to Purchaser role | Open | Under Development |  |  | This is not a defect, however we have added this a process increment in BTP.
3 | GRN | Legal Compliance Issues | Future GRN Entries | System is allowing to book future date GRN entries | Open | Financial & Compliance Risk |  | Yes
4 | GRN | Legal Compliance Issues | GRN Supportings | Attachment Option is greyed out for MIGO Entry or GRN Creations. No Authorization to attach documents during GR creation | Open | Audit observations & compliance Risk | 4500109912 |  | Already working and Yashoda has tried also from Fiori app.
5 | PO | Functional Defects | PO Copy Language | PO Headers coming in german language & not in english for vendors set up in Germany. Same to generalize to English | Open | PO Creator cannot read & interpret correctly on the PO requirements |  | Yes | Common topic for DIR/IND
6 | PO | Functional Defects | Role Mapping | PR approval role is mapped to PO creator Role in U4Q which may be a SOD conflict/observation . Same needs to be checked with correct role & mapped. (e.g GID- Z004HDYW) or possibility of eliminating the step creating duplication. | Open | SRE Business Stakeholders to provide Remarks
7 | PO | Functional Defects | HSN /SAC Code | HSN/SAC code allow to update in U4Q at PO level but does not reflect in PO print out (Item level) | Open | Under Discussion | 4500109623 | Yes | Common topic for DIR/IND
8 | PO | Issue Fixed | Tax Code | Tax Component breakup is not reflecting in PO printout line level | Open | UAT in progress due to developments confirmed on 14th Aug
9 | PO | Legal Compliance Issues | ESN Mapping | PR created using service ESN code accepts HSN code in the PO without any hard stop which is non complaint and high risk | Open | Financial Risk |  |  | All ESN are allowed, PR creator/purchaser has to make sure that correct ESN is used.
10 | PO | Functional Defects | PO Printout | PO Print out GTC & Local regulations with Format to be aligned | Open | Under Development | 4500109623 | Yes | Common topic for DIR/IND
11 | PO | Legal Compliance Issues | Currency Changes | When currency change is made from EUR to INR or vice versa , system accepts the same & does not trigger for any approval | Open | Financial Risk | 4500109912 |  | Standard S4 Behaviour in S4 and common topic for both INDX and DIRX.
12 | PO | Functional Defects | PO Status | After PO released to vendor the status is not reflecting in the PO visibility tab | Open | Addiitonal effort, Follow ups | 4500110232
13 | PO | Issue Fixed | TAX Value Calculations | PO Grand total value is reflecting with out tax value | Open | Addiitonal effort, Incorrect Billing, Financial Impact | 4500110232
14 | PO | Under Development | Vendor GSTIN & PAN | Vendor GSTIN and Pan number is not reflecting in the PO | Open | Under Development | 4500110232 | Yes
15 | PO | Issue Fixed | Tax Components & Break Up | If Vendor is intra- state in PO the tax to be applied is SGST & CGST , however the PO is reflecting with IGST incorectly | Open | UAT in progress due to developments confirmed on 14th Aug | 4500109972
16 | PO | Functional Defects | PO Ammendment | PO Amendment : The following PO Ammendment in UAT system and all these amendments PO's are relesaed with out PO approval. 1.Delivery date updated 2.Price reduced 3.ESN Changes 4.Currency changes 5.Tax code changes 6.Cost center change 7.Payment term changes | Open | Financial Risk | 1.4500109623 2.4500109952 3.4500109623 4.4500109912 5.4500109952 6.4500109952 7.4500109912 | Yes | PO release strategy will retrigger only in price increase , no other cretia.
17 | PO | Functional Defects | Special Tax rate | For supply of coke product tax rate is 40 % , we require a tax code to test tax rate | Open | Under Discussion | sample tax slab referred |  | Please align with Vertex resposible.
18 | PO | Process alignment topics | Line Item addition | While creating the PO the line item of PR's to be entered manually and auto capturing of all the line items is missing | Open | Additional Effort & TAT delay for PO creation, Follow ups | 4500110133
19 | PO | Process alignment topics | PO Supportings | Supporting documents cannot be attached on PO level but possible on line level | Open | Additional Effort & TAT delay for PO creations, Additional Follow ups & Customer Dis satisfaction | 4500109623
20 | PO | Process alignment topics | Supporting Creation | To create a document the PO buyer has to follow 7 steps to complete document (Back up Attachment) additional time involved | Open | Additional Effort & TAT delay for PO creations, Additional Follow ups & Customer Dis satisfaction
21 | PO | Process alignment topics | Line Item addition | PO Amendment : new line item addtition is possible or not for existing PO | Open | Additional Effort & TAT delay for PO creations, Additional Follow ups & Customer Dis satisfaction | 4500109623

## Indirect X UAT OBS
SL NO. | WF step (REQ, PO, APP, etc.) | Particular | Tested | Result | Implications | Referance
1 | REQ | GL Account Disappears when account assignment changed | GL Account disappears when account assignment changed from cost center to WBS | Open | 1. Manual intervention - Chances of Typo errors 2. Cost allocation will be inaccurate with incorrect GL's
2 | REQ | RFQ Module - Less than 15 lakh | 1. Multiple Vendor RFQ Test - Not yet tested because only a single Supply Chain (SC) entity exists in SCM Star. 2. SDD Document Creation - Not tested due to an error and missing linkage. - working fine with single vendor. | Open | Unsure on multiple vendor RFQ's since vendor details & SDD documents for testing are unavailable in SCM Star for GBS Buyer to validate | rfq_32205
3 | PO | RFQ Format | India Standard RFQ Format Shared with Project Team, Configuration to be completed by the Project Team and Testing to be conducted upon receipt of confirmation from the Project Team - Tested working flow using existing standard format | Open | Blockage at PO step
4 | APP | PO Copy Printout (Language) | PO Headers in PO Printout Copy reflects in German instead of english | Open | PO Creator cannot read & interpret correctly on the PO requirements | 4500109772 | No defect but topic for internal alignment based on SAP note
5 | PO | PR Approval by Purchaser | All Freetext & catalog PO's are routed from system today for PR approval to PO creator (Purchaser) once for PR approval at procurement verification step & then for PO creation which is a duplication of activity. | Open | Additional Effort
6 | PO | Overall Limit tab activated orTolerance Limit on PO | Overall Limit tab is active for PO creators & ideally should be deactive at procurement verification step since it allows unlimited GRN booking against PO value & is a risk | Open | Compliance Risk of overbooking GR/IR & Payment
7 | PO | HSN /SAC Code on PO | HSN/SAC code allow to update in U4Q at PO level but does not reflect in PO print out (Item level) | Open | Compliance Risk of of incorrect Tax booking & returns | 4500109899 | Not confirmed
8 | PO | TAX Component Break up | Tax component breakup is not reflecting in PO line item level & overall PO value level | Open | UAT In Progress due recent developments confirmed on 14th Aug | 4500109899
9 | PO | ESN code for Material/Service | PR created using service ESN code accepts HSN code in the PO meant for Material PO's without any hard stop which is non complaint and high risk | Open | Compliance Risk of of incorrect Tax booking & returns | 4500109880
10 | PO | Tax Component Testing | PO Created with multiple Tax code IGST SGST and CGST in one Single PO is accepting which is a high risk | Open | UAT In Progress due recent developments confirmed on 14th Aug | 4500109899
11 | PO | PO Type Selections | Selection of PO type (Material, Service, etc) options are available to select at Procurement verification step how ever it only allows to select Material type as only option even for services . (No other options in the drop down are selectable) | Open | If not implemented will lead to Incorrect categorization of PO type
12 | PO | Delivery date Observation | PR issued with expired delivery date currently allows to convert to PO which ideally should not allow.Delivery date (Delivery date falls under week end or week off day) | Open | Escalations & customer dis-satisfactions, PO TAT impact | 10381484
13 | PO | Currency Testing | When currency change is made from EUR to INR, system acceps the same & does not trigger for any approval | Open | Financial Risk | 4500109772
14 | PO |  | Cost Center Changes : cost center is changed on existing PO, system should ask approval from new CC owner how ever system acceps the same & does not trigger for any approval | Open | Financial Risk | 4500109880
15 | PO |  | Advance Payment: PT changed to 100% advance, system acceps the same & does not trigger for any approval | Open | Financial Risk | 4500109882
16 | PO |  | For all test scenarios where delivery date changed, Price reduced to lower value, ESN code changed & plant code changed system accepts the same without any trigger for approval or hardstop | Open | Financial Risk,Incorrect Material Spend | 4500109772 4500109721 4500109723 4500109769 4500109817
17 | PO |  | When PO is ammended, system does not trigger for approval to CAT approvers for applicable ammendment type. Upon check with Indirect X Roll out Spoc, we understand that manual E-mail approval has to be taken from the approvers and proceed ammendment & attach the supportings. Need to be clarified by when the auto approval triggers to approvers will be inbuilt in SX? | Open | Effort increase, Manual intervention
18 | PO | Failure of PO copy Transmission | Approved PO copy delivery to vendor - If the vendor mail ID is inactive & bouncing back should trigger an error message in indirect X highlilighting on unsuccessful transmission to be clear whether vendor received the PO copy or not. | Open | Delay in PO confirmation, Delivery & additional follow ups/Esc
19 | PO | PO Reporting | Procedure to download Open PR & PO report with Saved PO status report to be confirmed | Open | Productivity monitoring & control review
20 | PO | Vendor GST IN & PAN # on PO printout | Vendor GSTIN and PAN number is not reflecting in the PO | Open | Incorrect Billing & Financial Impact |  | No confirmed
21 |  | PO Printout | PO Print out GTC & Local regulations with Format to be aligned | Open | UAT In Progress due recent developments confirmed on 14th Aug |  | No confirmed