## Sheet1
Incident Management | Case Management (L1) | Incident Management (L2-L3)
Service Level Management | Contracts & SLA tracking
Change Management | With SX Project
Monitoring & Event Management | Analytics & Reporting
Continual Improvement | ?
Service Design | Advanced Execution Planning
Service Integration | List of all interfaces | myMall
MDG/GMDM
BTP
GTS
VERTEX

## Sheet2
Operational Setup Phases |  | Status
1. Define Service Strategy | Identify business goals and service offerings.
Align with ITIL 4’s Service Value System (SVS).
Define KPIs and SLAs for services.
2. Design Service Processes | Use SAP S/4HANA’s Service Management module to model:
Service contracts
Service orders
Resource planning
Integrate with ITIL practices like Service Design, Capacity Management, and Availability Management.
3. Configure SAP S/4HANA | Activate relevant service management components.
Set up:
Service products
Service order types
Billing profiles
DIP profiles (for dynamic item processing)
Define organizational units (service org, plant, etc.).
4. Integrate SAP BTP | Use SAP BTP for:
Extending service apps (CAP, RAP)
Workflow automation
Event-driven architecture
Analytics and dashboards
Ensure connectivity via SAP Cloud Connector or BTP destinations.
5. Enable ITIL 4 Practices | Map SAP processes to ITIL practices:
Incident Management → Service Requests
Problem Management → Root cause analysis via analytics
Change Enablement → Service order lifecycle
Monitoring & Event Management → BTP dashboards
Continual Improvement → Feedback loops and KPI tracking
6. Train & Onboard Teams | Define roles: Service Manager, Dispatcher, Technician, Analyst.
Provide training on SAP UI5/Fiori apps and BTP extensions.
Align team responsibilities with ITIL roles.
7. Go-Live & Monitor | Conduct UAT and pilot runs.
Monitor service performance using embedded analytics.
Use SAP BTP’s Alert Notification Service and SAP Analytics Cloud for real-time insights.
✅ Key Considerations
Area | Consideration
Governance | Align with ITIL 4 governance model and compliance standards.
Security | Use SAP Identity Authentication and Authorization (IAS/IPS).
Scalability | Design services to scale with business growth.
Integration | Ensure seamless data flow between S/4HANA, BTP, and third-party systems.
Automation | Leverage BTP workflows and bots for repetitive tasks.
User Experience | Use Fiori apps and custom BTP apps for intuitive service handling.
Data Quality | Maintain master data integrity for customers, equipment, and services.