## FO only service
SL No | Date | Reference number | Test Description | Task | Responsibility | Status | Observation | Solution
1 | 2025-08-08 | PR - 10393768 | Submit PR with service on Behalf (< 50K EUR), For 3P vendor | *PR submitted for service * Submitted the FO PR | Samiksha | Passed
2 | 2025-08-08 | PR - 10393768 | Submit PR with service on Behalf (< 50K EUR), For 3P vendor | PR has been approved | Samiksha | Passed | PR Approval is trrigring to the PR creator
3 | 2025-08-08 | PR - 10393768 | Submit PR with service on Behalf (< 50K EUR), For 3P vendor | Approve the PR | Samiksha | Passed | Approval is trrigring to the Buyer
4 | 2025-08-08 | PR - 10393768 | Submit PR with service on Behalf (< 50K EUR), For 3P vendor | * Buyer validate the PR * If incorrect reject the PR * If correct Send RFQ through email * Get the quotes * Update the prices, Purchasing Group & supplier details mannually in the PR for each line item. * HSN or SAC to be provided as a attachement * Buyer approves the PR | Priyanka | Passed | *Supplier details to be taken from GMDM Tool, drop down menu is there in PR to select the supplier but all revelant details like full address, payment terms etc not visible * PR Approval is trrigring to the Purchaser
5 | 2025-08-08 | PR - 10393768 | Submit PR with service on Behalf (< 50K EUR), For 3P vendor | * Purchaser validate the PR * If incorrect reject the PR * If correct Purchaser approve the PR * Purchaser will create PO | Zohaib | Passed | Approval is trrigring to the PR creator as a notification
6 | 2025-08-08 | PR - 10393768, PO - 4500109952 | Submit PR with service/material on Behalf (< 50K EUR), For 3P vendor | *Purchaser has to select Direct FO PO * For service SAC code need to be updated in India tab * Tax code is auto capctured by the system when with update the control Code | Zohaib | Passed
7 | 2025-08-08 | PR - 10393768, PO - 4500109952 | Submit PR with service/material on Behalf (< 50K EUR), For 3P vendor | Print Preview | Zohaib | Failed | *SAC is not reflecting in the PO & Print preview *Tax percentage is not reflecting in the PO & Print preview
8 | 2025-08-08 | PR - 10393768, PO - 4500109952 | Submit PR with service/material on Behalf (< 50K EUR), For 3P vendor | PO Approval | Zohaib | Failed | Purchaser role - Unable to download PO copies (GID- Z004HDYW) with Purchaser role assigned.
9 | 2025-08-08 | PR - 10393768, PO - 4500109952 | Submit PR with service/material on Behalf (< 50K EUR), For 3P vendor | PO Approval | Zohaib | Failed | PR approval role is mapped to PO creator/Purchaser Role in U4Q which may be a SOD conflict/observation . Same needs to be checked with correct role & mapped. (e.g GID- Z004HDYW) or possibility of eliminating the step creating duplication.
10 | 2025-08-08 | PR - 10393768, PO - 4500109952 | Submit PR with service/material on Behalf (< 50K EUR), For 3P vendor | PO Approval | Zohaib | Failed | MSME Payment terms no system hardstop & allows manual PT change - Risk is 45 days payment terms /allowable payment terms for MSME suppliers only should reflect in PO and auto mapped in backend not allowing for manual PT change for compliance adherences.
11 | 2025-08-08 | PR - 10393768, PO - 4500109952 | Submit PR with service/material on Behalf (< 50K EUR), For 3P vendor | PO Approval | Zohaib | Failed | PR created using service ESN code accepts HSN code in the PO without any hard stop which is non complaint and high risk (part of negative testing)
12 | 2025-08-08 | PR - 10393768, PO - 4500109952 | Submit PR with service/material on Behalf (< 50K EUR), For 3P vendor | PO Creations | Zohaib | Failed | PO approver names not reflecting in PO copy (functional & commercial approvers)
13 | 2025-08-08 | PR - 10393768, PO - 4500109952 | Submit PR with service/material on Behalf (< 50K EUR), For 3P vendor | PO Creations | Zohaib | Failed | When PR is fully released, no notification via mail received to Purchaser to proceed PO creations. Same to check for enabling in the backend.

## NB Standard
SL No | Date | Reference number | Test Description | Task | Responsibility | Status | Observation | Solution
1 | 2025-08-08 | PR - 10393811 | Submit PR with service/material on Behalf (< 50K EUR), For 3P vendor | *PR submitted for material and services 3 line items are material and 1 service. *Used the Combination of cost center and WBS * Submitted the NB standard PR | Samiksha | Passed
2 | 2025-08-08 | PR - 10393811 | Submit PR with service/material on Behalf (< 50K EUR), For 3P vendor | PR has been approved | Samiksha | Passed | PR Approval is trrigring to the PR creator
3 | 2025-08-08 | PR - 10393811 | Submit PR with service/material on Behalf (< 50K EUR), For 3P vendor | Approve the PR | Samiksha | Passed | Approval is trrigring to the Buyer
4 | 2025-08-08 | PR - 10393811 | Submit PR with service/material on Behalf (< 50K EUR), For 3P vendor | * Buyer validate the PR * If incorrect reject the PR * If correct Send RFQ through email * Get the quotes * Update the prices, Purchasing Group & supplier details mannually in the PR for each line item. * HSN or SAC to be provided as a attachement * Buyer approves the PR | Priyanka | Passed | *Supplier details to be taken from GMDM Tool, drop down menu is there in PR to select the supplier but all revelant details like full address, payment terms etc not visible * PR Approval is trrigring to the Purchaser
5 | 2025-08-08 | PR - 10393811 | Submit PR with service/material on Behalf (< 50K EUR), For 3P vendor | * Purchaser validate the PR * If incorrect reject the PR * If correct Purchaser approve the PR * Purchaser will create PO | Zohaib | Passed | Approval is trrigring to the PR creator as a notification
6 | 2025-08-08 | PR - 10393811, PO - 4500109956 | Submit PR with service/material on Behalf (< 50K EUR), For 3P vendor | *Purchaser has to select YDNB Direct PO or YDFO Direct FO PO *For material HSN code need to be updated in India tab * For service SAC code need to be updated in India tab * Tax code is auto capctured by the system when with update the control Code | Zohaib | Passed
7 | 2025-08-08 | PR - 10393811, PO - 4500109956 | Submit PR with service/material on Behalf (< 50K EUR), For 3P vendor | Print Preview | Zohaib | Passed | *HSN and SAC is not reflecting in the PO & Print preview *Tax percentage is not reflecting in the PO & Print preview
8 | 2025-08-08 | PR - 10393811, PO - 4500109956 | Submit PR with service/material on Behalf (< 50K EUR), For 3P vendor | PO Approval | Zohaib | Passed
9 | 2025-08-08 | PR - 10393811, PO - 4500109956 | Submit PR with service/material on Behalf (< 50K EUR), For 3P vendor | PO Approval | Zohaib | Passed | Purchaser role - Unable to download PO copies (GID- Z004HDYW) with Purchaser role assigned.
10 | 2025-08-08 | PR - 10393811, PO - 4500109956 | Submit PR with service/material on Behalf (< 50K EUR), For 3P vendor | PO Approval | Zohaib | Passed | PR approval role is mapped to PO creator/Purchaser Role in U4Q which may be a SOD conflict/observation . Same needs to be checked with correct role & mapped. (e.g GID- Z004HDYW) or possibility of eliminating the step creating duplication.
11 | 2025-08-08 | PR - 10393811, PO - 4500109956 | Submit PR with service/material on Behalf (< 50K EUR), For 3P vendor | PO Approval | Zohaib | Passed | MSME Payment terms no system hardstop & allows manual PT change - Risk is 45 days payment terms /allowable payment terms for MSME suppliers only should reflect in PO and auto mapped in backend not allowing for manual PT change for compliance adherences.
12 | 2025-08-08 | PR - 10393811, PO - 4500109956 | Submit PR with service/material on Behalf (< 50K EUR), For 3P vendor | PO Approval | Zohaib | Passed | PR created using service ESN code accepts HSN code in the PO without any hard stop which is non complaint and high risk
13 | 2025-08-08 | PR - 10393768, PO - 4500109952 | Submit PR with service/material on Behalf (< 50K EUR), For 3P vendor | PO Creations | Zohaib | Failed | PO approver names not reflecting in PO copy (functional & commercial approvers)
14 | 2025-08-08 | PR - 10393768, PO - 4500109952 | Submit PR with service/material on Behalf (< 50K EUR), For 3P vendor | PO Creations | Zohaib | Failed | When PR is fully released, no notification via mail received to Purchaser to proceed PO creations. Same to check for enabling in the backend.
15 | 2025-08-08 | 4500109623 | GRN | Print Preview | Yashodha | Passed | No access to print preview, copy can be downloaded, NO HSN/SAC
16 | 2025-08-08 | 4500109623 | GRN | GRN creation | Yashodha | Passed | No attachment possible at GRN level.
17 | 2025-08-08 | 4500109623 | GRN | GRN creation | Yashodha | Passed | Allowed for GRN creation with future document date
18 | 2025-08-08 | 4500109623 | GRN | GRN creation | Yashodha | Passed | No Duplicate check
19 | 2025-08-08 | 4500109623 | GRN | GRN creation | Yashodha | Passed
20 | 2025-08-08 | 4500109952 | GRN | GRN creation | Yashodha | Passed | No Other Option in the reasons for 122 movement

## FO with material,Service
SL No | Date | Reference number | Test Description | Task | Responsibility | Status | Observation | Solution
1 | 2025-08-08 | PR - 10395450 | Submit PR with service/material on Behalf (< 50K EUR), For 3P vendor | *PR submitted for material and services 1 line items are material and 1 service. *Used the WBS * Submitted the FO PR | Samiksha | Passed
2 | 2025-08-08 | PR - 10395450 | Submit PR with service/material on Behalf (< 50K EUR), For 3P vendor | PR has been approved | Samiksha | Passed | PR Approval is trrigring to the PR creator
3 | 2025-08-08 | PR - 10395450 | Submit PR with service/material on Behalf (< 50K EUR), For 3P vendor | Approve the PR | Samiksha | Passed | Approval is trrigring to the Buyer
4 | 2025-08-08 | PR - 10395450 | Submit PR with service/material on Behalf (< 50K EUR), For 3P vendor | * Buyer validate the PR * If incorrect reject the PR * If correct Send RFQ through email * Get the quotes * Update the prices, Purchasing Group & supplier details mannually in the PR for each line item. * HSN or SAC to be provided as a attachement * Buyer approves the PR | Priyanka | Passed | *Supplier details to be taken from GMDM Tool, drop down menu is there in PR to select the supplier but all revelant details like full address, payment terms etc not visible * PR Approval is trrigring to the Purchaser
5 | 2025-08-08 | PR - 10395450 | Submit PR with service/material on Behalf (< 50K EUR), For 3P vendor | * Purchaser validate the PR * If incorrect reject the PR * If correct Purchaser approve the PR * Purchaser will create PO | Zohaib | Passed | Approval is trrigring to the PR creator as a notification
6 | 2025-08-08 | PR - 10395450, PO - 4500109968 | Submit PR with service/material on Behalf (< 50K EUR), For 3P vendor | *Purchaser has to select Direct FO PO *For material HSN code need to be updated in India tab * For service SAC code need to be updated in India tab * Tax code is auto capctured by the system when with update the control Code | Zohaib | Passed
7 | 2025-08-08 | PR - 10395450, PO - 4500109968 | Submit PR with service/material on Behalf (< 50K EUR), For 3P vendor | Print Preview | Zohaib | Passed | *HSN and SAC is not reflecting in the PO & Print preview *Tax percentage is not reflecting in the PO & Print preview
8 | 2025-08-08 | PR - 10395450, PO - 4500109968 | Submit PR with service/material on Behalf (< 50K EUR), For 3P vendor | PO Approval | Zohaib | Passed
9 | 2025-08-08 | PR - 10395450, PO - 4500109968 | Submit PR with service/material on Behalf (< 50K EUR), For 3P vendor
10
11 | 2025-08-08 | PR - 10395450, PO - 4500109968 | Submit PR with service/material on Behalf (< 50K EUR), For 3P vendor | PO Approval | Zohaib | Passed | PR approval role is mapped to PO creator/Purchaser Role in U4Q which may be a SOD conflict/observation . Same needs to be checked with correct role & mapped. (e.g GID- Z004HDYW) or possibility of eliminating the step creating duplication.
12 | 2025-08-08 | PR - 10395450, PO - 4500109968 | Submit PR with service/material on Behalf (< 50K EUR), For 3P vendor | PO Approval | Zohaib | Passed | MSME Payment terms no system hardstop & allows manual PT change - Risk is 45 days payment terms /allowable payment terms for MSME suppliers only should reflect in PO and auto mapped in backend not allowing for manual PT change for compliance adherences.
13 | 2025-08-08 | PR - 10395450, PO - 4500109968 | Submit PR with service/material on Behalf (< 50K EUR), For 3P vendor | PO Approval | Zohaib | Passed | PR created using service ESN code accepts HSN code in the PO without any hard stop which is non complaint and high risk
14 | 2025-08-08 | PR - 10393768, PO - 4500109952 | Submit PR with service/material on Behalf (< 50K EUR), For 3P vendor | PO Creations | Zohaib | Failed | PO approver names not reflecting in PO copy (functional & commercial approvers)
15 | 2025-08-08 | PR - 10393768, PO - 4500109952 | Submit PR with service/material on Behalf (< 50K EUR), For 3P vendor | PO Creations | Zohaib | Failed | When PR is fully released, no notification via mail received to Purchaser to proceed PO creations. Same to check for enabling in the backend.
16 | 2025-08-08 | 4500109623 | GRN | Print Preview | Yashodha | Passed | No access to print preview, copy can be downloaded, NO HSN/SAC
17 | 2025-08-08 | 4500109623 | GRN | GRN creation | Yashodha | Passed | No attachment possible at GRN level.
18 | 2025-08-08 | 4500109623 | GRN | GRN creation | Yashodha | Passed | Allowed for GRN creation with future document date
19 | 2025-08-08 | 4500109623 | GRN | GRN creation | Yashodha | Passed | No Duplicate check
20 | 2025-08-08 | 4500109623 | GRN | GRN creation | Yashodha | Passed
21 | 2025-08-08 | 4500109952 | GRN | GRN creation | Yashodha | Passed | No Other Option in the reasons for 122 movement